2th June 2025

# We’re investing to upgrade the power supply

Hello. We’re Electricity North West and we operate your local electricity network.

Over the next 18 months, we are carrying out crucial upgrades on the power network in Salford, investing £11.6m.

The work we are carrying out will see new underground electricity cables installed as well as new equipment installed and upgrades carried out at local substations. The work will benefit 24,000 homes and businesses and allow for more people to connect low carbon technologies such as electric vehicle charges and heat pumps.

A lot of our network was installed back in the 1950s and 60s so it is vital work happens now as we become more reliant on electricity. We are working closely with the local authorities to minimise disruption.

Work is expected to start next week and we have detailed the first four weeks of the programme. Temporary traffic lights will be used to ensure teams can work safely in the highway.

# How this will affect you

* Team 1 engineers will start work on June 9th 2025 at Frederick Road adjacent to David Lewis Park and progress to Gerald Road, work will approximately take 5 weeks
* Teams will carry out work at the following:
  + *Frederick Road 09/06/25 for approximately 3 days with multi way traffic lights*
  + Seaford Road 11/06/25 for approximately 20 days with two way/multi way traffic lights
  + Gerald Road 30/6/25 for approximately 10 days with two way traffic lights
* Side Road Closures
* Welford Street (23/06/25)
* Coniston Street (25/06/25)
* Haddon Street (02/07/25)
* Beeley Street (04/07/25)
* Rowsley Street (08/07/25)
* Access to properties will be maintained throughout all of the project
* All works taking place have been agreed with the local council
* Local electricity supplies should not be affected by the works

Throughout the project, we’ll do our best to keep disruption to a minimum.

Please do get in touch if you have any queries.

Jane Newton   
Project Engineer